## Burndown Template
Burndown:
|  |  | Thu | Fri | Sat | Sun | Mon | Tue | Wed
Task | Allocated To: | Total Hours Required | 2013-08-22 | 2013-08-23 | 2013-08-24 | 2013-08-25 | 2013-08-26 | 2013-08-27 | 2013-08-28
Story 06: Re-centre to Postcode
Review Google’s Map API | Tom, Mike | 2 | 2 | 0 | 0 | 1 | 0 | 0 | 0
Write Test cases | Tom, Mike | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Textbox receives and checks postcode information | Tom, Mike | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
Reposition map to inputted position | Tom, Mike | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
Run Selenium test(s) | Tom, Mike | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0
Verify story is complete (acceptance test) | ALL | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Story 14: Search Results (publication)
Get Meta-Data | Alex, Leander | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Write Test cases | Alex, Leander | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Create publication name Textbox | Alex, Leander | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Write code to restrict search query | Alex, Leander | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0
Check and enhance results | Alex, Leander | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Verify story is complete (acceptance test) | ALL | 1 | bar: 2013-08-22 to 2013-08-28
Story 23: Focused Search
Get Meta-Data | Turk, Steven | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Write Test cases | Turk, Steven | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Create postcode Textbox | Turk, Steven | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Code to limit results with given postcode | Turk, Steven | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 3
Verify story is complete (acceptance test) | ALL | 1 | bar: 2013-08-22 to 2013-08-28
| Total remaining hours | 28 | 28 | 23 | 23 | 19 | 16 | 12 | 11
| Change in hours |  |  | -5 | 0 | -4 | -3 | -4 | -1
| Ideal Burndown: | 28 | 28 | 23.3333 | 18.6667 | 14 | 9.3333 | 4.6667 | 0